## Sponsor Inputs
# | High level ideas / Features
1 | Create Account
2 | View Restaurants
3 | Search Restaurants
4 | View Menu
5 | Add to Cart
6 | Purchase
7 | Restaurant views order
8 | Restaurant marks order as delivered
Notes:
1 | The above points were listed as draft ideas by the project sponsor.
2 | The project sponsor mentioned that he wants to compete against Talabat.
3 | As a sponsor, I am planning to compete against Talabat.
4 | This is a view only file, you can make a copy then edit in the copy.
5 | You can find a tab named Product Backlog Template, please feel free to use it when creating your product backlog.

## Product Backlog Template
# | Epic | User Story | Priority | Ready to be planned | Planned Sprint | Status
As a < type of user >, I want < some goal > so that < some reason >
| 1 | as a product owner I want the cumstomer to create an account to order food | High 5 | Must | 1 | Done
| 2 | as a product owner I want the customer to see the resturents to start to order food | High 5 | Must | 1 | Done
| 3 | as a product owner I want the customer pick from the catogarys to see the resturants | Med 3 | Could | 1 | Done
| 4 | as a product owner I want the cutomer to see the menu so that’s he can pick food | Med 3 | Could | 1 | work in progress
| 5 | as a product owner I want the customer to add the item he pick to the cart | High 5 | should | 1 | work in progress
| 6 | as a product owner I want the customer to purchase so that can complete the order | High 5 | should | 1 | work in progress
| 7 | as a product owner I want the customer to be able to choose payment opstions cash or card | High 5 | should | 2 | work in progress
| 8 | as a product owner I want the restaurant to view order to make the customer order is perpared | High 5 | should | 3 | to be started
| 9 | as a product owner I want the restaurant to mark as delieverd so that get notfication of finish order | Med 3 | should | 3 | to be started