## Risk Register
RISK REGISTER
REF ID | RISK | RISK OWNER | RISK TRIGGER | RISK CATEGORY | PROBABILITY 1 – 3 | IMPACT 1 – 3 | PI SCORE Prob x Impact | EXPECTED RESULT ¦ NO ACTION | POSITIVE RISK RESPONSE | NEGATIVE RISK RESPONSE | RESPONSE TRIGGER | RESPONSE OWNER | RESPONSE DESCRIPTION | EXPECTED RESPONSE IMPACT | PROBABILITY 1 – 3 KEY | IMPACT 1 – 3 KEY | POSITIVE RISK RESPONSE | NEGATIVE RISK RESPONSE
1 | Low traffic and customer count | Project manager | Launch of application | Risk to BAU | 2 | 3 | 6 | Losses to the company |  | MITIGATE | Before launh of applicarion by 1 week | Media team | Increase awareness of new product by conducting mulitple ad campaigns | PI score redcued to 1, can be accepted | 1 | 1 | ACCEPT | ACCEPT
2 | Functions not wokring as planned | Project manager | Bugs found | Risk to BAU | 1 | 3 | 3 | Losses to the company |  | MITIGATE | Before launch | Project manager | Mulitple trouble shooting and testing sessions | PI score reduced to 1, can be accepted | 2 | 2 | ENHANCE | MITIGATE
3 | Not meeting deadlines | Project manager | Delays in schedule | Risk to project | 1 | 2 | 2 | Delayed profits |  | MITIGATE | when progres is not going as plan | Project manager | Close monitoring of progress by receiving daily reports on progress and issues that may affect it. | PI score reduced to 1, can be accepted | 3 | 3 | SHARE | TRANSFER
4 | lost users data | development team | Notification of lost data | Risk to BAU | 2 | 3 | 6 | Losses to the company |  | TRANSFER | Notification of lost data | development team | development team to rectify | PI score reduced to 1, can be accepted |  |  | EXPLOIT | AVOID
5 | denial of services | development team | The applcation stop working | Risk to project | 2 | 3 | 6 | Delayed profits |  | TRANSFER | The applcation stop working | development team | development team to rectify | PI score reduced to 1, can be accepted
6 | weak authentication | development team | Notification of weak authentication | Risk to project | 1 | 3 | 3 | Delayed profits |  | TRANSFER | Notification of weak authentication | development team | development team to rectify | PI score reduced to 1, can be accepted
7 | security malfunction | development team | Notification of security malfunction | Risk to project | 2 | 3 | 6 | Delayed profits |  | TRANSFER | Notification of security malfunction | development team | development team to rectify | PI score reduced to 1, can be accepted
8 | missing function level | development team |  | Risk to project | 1 | 3 | 3 | Delayed profits |  | TRANSFER |  | development team | development team to rectify | PI score reduced to 1, can be accepted
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
CLICK HERE TO CREATE IN SMARTSHEET