## Proposal
Discount Card Cost estimate +/- 10%
QUANTITY | DESCRIPTION | UNIT PRICE | Hours | AMOUNT
1 | Project Manager | 70 | 360 | 25200
3 | Team leader | 30 | 360 | 32400
9 | Team members | 15 | 360 | 48600
1 | Apple store, google store subscriptions | 1000 | 1 | 1000
3 | Permits | 1000 | 1 | 3000
4 | Traveling allowance | 1000 | 1 | 4000
|  | SUBTOTAL |  | 114200
The assumptions to above cost estimate are |  | Contingency |  | 5%
No delays to the schedule All permits received in timely fashion Media coverage and adviretisment not included in estimation 2 Design review meetings shall be held face-to-face Works on IT infrastrcuture not included Working hours are 12 hours/ day, 6 days a week Any additional scope will be subject to change notice and increase in total cost |  | Contingency amount |  | 5710
OTHER
|  | TOTAL |  | 119910